## Master Data
ADANI GREEN ENERGY LIMITED — Project Master Tracker
Project ID | Project Name | Project Type | Location | State | Capacity (MW) | FY Year | Category | Budget Allocated (₹ Cr) | Budget Used (₹ Cr) | Budget Remaining (₹ Cr) | Revenue Generated (₹ Cr) | Scheduled Comm. Date | Expected Comm. Date | Actual Comm. Date | Contractor Name | Material (Module/Turbine) | Material Status | Contractor Payment Status | Project Completion (%) | Delay (Days) | Remarks
AGEL-S-001 | Tumkur Solar Phase 3 – 200MW | Solar | Tumkur | Karnataka | 200 | FY2023-24 | Commissioned | 983.75 | 926.94 | 56.81 | 262.59 | 12-Apr-2023 | — | 10-May-2023 | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-002 | Chitradurga Solar Park – 250MW | Solar | Chitradurga | Karnataka | 250 | FY2022-23 | Commissioned | 1201.97 | 1140.33 | 61.64 | 257.7 | 18-Jul-2021 | — | 29-Jul-2021 | Sterling and Wilson Pvt Ltd | Jinko Solar (545W Tiger Neo) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-003 | Pokhran Solar Phase 2 – 100MW | Solar | Pokhran | Rajasthan | 100 | FY2021-22 | Commissioned | 518.96 | 513.22 | 5.74 | 123.38 | 05-Jun-2022 | — | 24-Aug-2022 | Sterling and Wilson Pvt Ltd | Trina Solar (550W Vertex) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-004 | Jodhpur Solar Phase 1 – 250MW | Solar | Jodhpur | Rajasthan | 250 | FY2021-22 | Commissioned | 1231.36 | 1215.02 | 16.34 | 241.67 | 14-Jan-2023 | — | 18-Feb-2023 | KEC International | LONGi Solar (555W Hi-MO6) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-005 | Mundra Solar Phase 1 – 100MW | Solar | Mundra | Gujarat | 100 | FY2023-24 | Commissioned | 493.96 | 465.11 | 28.85 | 134.62 | 27-Apr-2022 | — | 17-May-2022 | Vikram Solar Ltd | Waaree Energies (550W Mono PERC) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-006 | Patan Solar Phase 2 – 200MW | Solar | Patan | Gujarat | 200 | FY2022-23 | Commissioned | 907.51 | 903.37 | 4.14 | 242.88 | 25-Jun-2022 | — | 03-Jul-2022 | KEC International | Jinko Solar (545W Tiger Neo) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-007 | Osmanabad Solar Phase 3 – 400MW | Solar | Osmanabad | Maharashtra | 400 | FY2022-23 | Commissioned | 1769.36 | 1733.26 | 36.1 | 413.85 | 17-Sep-2021 | — | 20-Oct-2021 | Genus Power Infrastructures | Canadian Solar (550W HiKu7) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-008 | Morbi Solar Park – 300MW | Solar | Morbi | Gujarat | 300 | FY2021-22 | Commissioned | 1303.64 | 1204.26 | 99.38 | 248.95 | 08-Sep-2023 | — | 10-Nov-2023 | Goldi Solar Pvt Ltd | REC Group (405W Alpha Pure-R) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-009 | Anantapur Solar Park – 100MW | Solar | Anantapur | Andhra Pradesh | 100 | FY2023-24 | Commissioned | 460.23 | 443.78 | 16.45 | 126.21 | 11-Jun-2023 | — | 17-Aug-2023 | SPML Infra Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-010 | Rann of Kutch Solar Park – 300MW | Solar | Rann of Kutch | Gujarat | 300 | FY2022-23 | Commissioned | 1261.56 | 1233.51 | 28.05 | 317.87 | 23-Sep-2021 | — | 20-Nov-2021 | SPML Infra Ltd | Adani Solar (540W TOPCon) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-011 | Jaisalmer Solar Phase 3 – 250MW | Solar | Jaisalmer | Rajasthan | 250 | FY2023-24 | Commissioned | 1199.57 | 1119.11 | 80.46 | 330.3 | 24-Jan-2022 | — | 12-Feb-2022 | Genus Power Infrastructures | JA Solar (545W DeepBlue) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-012 | Kurnool Solar Park – 500MW | Solar | Kurnool | Andhra Pradesh | 500 | FY2022-23 | Commissioned | 2146.34 | 2125.39 | 20.95 | 589.59 | 23-Aug-2022 | — | 22-Sep-2022 | Montecarlo Ltd | Adani Solar (540W TOPCon) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-013 | Bikaner Solar Park – 150MW | Solar | Bikaner | Rajasthan | 150 | FY2022-23 | Commissioned | 756.64 | 732.83 | 23.81 | 209.16 | 02-Nov-2021 | — | 05-Dec-2021 | Waaree Energies Ltd | Canadian Solar (550W HiKu7) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-014 | Pavagada Solar Phase 3 – 300MW | Solar | Pavagada | Karnataka | 300 | FY2022-23 | Commissioned | 1367.85 | 1295.42 | 72.43 | 326.68 | 05-Aug-2021 | — | 05-Sep-2021 | Genus Power Infrastructures | Trina Solar (550W Vertex) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-015 | Dhule Solar Park – 50MW | Solar | Dhule | Maharashtra | 50 | FY2023-24 | Commissioned | 215.39 | 198.7 | 16.69 | 45.89 | 02-Apr-2021 | — | 01-May-2021 | Waaree Energies Ltd | Jinko Solar (545W Tiger Neo) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-016 | Barmer Solar Phase 3 – 200MW | Solar | Barmer | Rajasthan | 200 | FY2023-24 | Commissioned | 1091.08 | 1074.28 | 16.8 | 217.17 | 27-Jul-2023 | — | 27-Aug-2023 | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-017 | Khavda Solar Phase 3 – 400MW | Solar | Khavda | Gujarat | 400 | FY2021-22 | Commissioned | 1937.68 | 1835.26 | 102.42 | 515.75 | 14-Jul-2021 | — | 21-Jul-2021 | KEC International | Trina Solar (550W Vertex) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-018 | Fatehgarh Solar Park – 500MW | Solar | Fatehgarh | Rajasthan | 500 | FY2021-22 | Commissioned | 2299.85 | 2285.73 | 14.12 | 515.89 | 27-May-2022 | — | 25-Jul-2022 | Sterling and Wilson Pvt Ltd | First Solar (440W Series 6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-019 | Tumkur Solar Phase 1 – 50MW | Solar | Tumkur | Karnataka | 50 | FY2021-22 | Commissioned | 248.51 | 245.82 | 2.69 | 67.16 | 10-Feb-2023 | — | 13-Apr-2023 | Goldi Solar Pvt Ltd | Waaree Energies (550W Mono PERC) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-020 | Chitradurga Solar Park – 400MW | Solar | Chitradurga | Karnataka | 400 | FY2022-23 | Commissioned | 2125.82 | 2079.99 | 45.83 | 549.18 | 15-Jun-2022 | — | 08-Aug-2022 | L&T Construction | Trina Solar (550W Vertex) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-021 | Pokhran Solar Park – 250MW | Solar | Pokhran | Rajasthan | 250 | FY2021-22 | Commissioned | 1072.87 | 1037.18 | 35.69 | 247.07 | 26-Mar-2021 | — | 05-May-2021 | Sterling and Wilson Pvt Ltd | First Solar (440W Series 6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-022 | Jodhpur Solar Phase 1 – 100MW | Solar | Jodhpur | Rajasthan | 100 | FY2023-24 | Commissioned | 557.89 | 531.28 | 26.61 | 152.95 | 23-Feb-2021 | — | 20-May-2021 | Genus Power Infrastructures | REC Group (405W Alpha Pure-R) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-023 | Mundra Solar Phase 2 – 50MW | Solar | Mundra | Gujarat | 50 | FY2023-24 | Commissioned | 284.78 | 266.65 | 18.13 | 71.66 | 28-Oct-2023 | — | 07-Dec-2023 | Waaree Energies Ltd | Canadian Solar (550W HiKu7) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-024 | Patan Solar Phase 2 – 150MW | Solar | Patan | Gujarat | 150 | FY2022-23 | Commissioned | 632.24 | 613.08 | 19.16 | 149.4 | 01-Oct-2022 | — | 10-Oct-2022 | Tata Projects Ltd | First Solar (440W Series 6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-025 | Osmanabad Solar Phase 1 – 200MW | Solar | Osmanabad | Maharashtra | 200 | FY2022-23 | Commissioned | 958.25 | 893.68 | 64.57 | 252.38 | 20-Apr-2021 | — | 21-May-2021 | Genus Power Infrastructures | First Solar (440W Series 6) | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-S-026 | Morbi Solar Phase 3 – 50MW | Solar | Morbi | Gujarat | 50 | FY2022-23 | Commissioned | 231.16 | 229.12 | 2.04 | 58.77 | 15-Jul-2021 | — | 01-Aug-2021 | Waaree Energies Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-027 | Anantapur Solar Phase 1 – 200MW | Solar | Anantapur | Andhra Pradesh | 200 | FY2023-24 | Commissioned | 996.33 | 988.78 | 7.55 | 263.64 | 22-Apr-2022 | — | 25-Jun-2022 | Goldi Solar Pvt Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-028 | Rann of Kutch Solar Park – 50MW | Solar | Rann of Kutch | Gujarat | 50 | FY2021-22 | Commissioned | 269.3 | 259.64 | 9.66 | 59.99 | 01-Jun-2022 | — | 21-Jun-2022 | Tata Projects Ltd | Adani Solar (540W TOPCon) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-029 | Jaisalmer Solar Phase 2 – 150MW | Solar | Jaisalmer | Rajasthan | 150 | FY2023-24 | Commissioned | 660.59 | 624.03 | 36.56 | 178.29 | 06-Sep-2021 | — | 31-Oct-2021 | Vikram Solar Ltd | Trina Solar (550W Vertex) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-030 | Kurnool Solar Phase 2 – 200MW | Solar | Kurnool | Andhra Pradesh | 200 | FY2023-24 | Commissioned | 1079.83 | 1073.42 | 6.41 | 219.93 | 24-Jan-2023 | — | 13-Apr-2023 | L&T Construction | Canadian Solar (550W HiKu7) | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-S-031 | Bikaner Solar Park – 50MW | Solar | Bikaner | Rajasthan | 50 | FY2025-26 | Ongoing | 250.24 | 163.73 | 86.51 | 0 | 26-Feb-2026 | 19-Oct-2026 | — | Tata Projects Ltd | Canadian Solar (550W HiKu7) | Partially Delivered – 25% | 50% Paid – Milestone 2 Pending | 51% | 235 | Land acquisition in progress
AGEL-S-032 | Pavagada Solar Park – 500MW | Solar | Pavagada | Karnataka | 500 | FY2025-26 | Ongoing | 2615.4 | 1907.22 | 708.18 | 0 | 25-Dec-2025 | 12-Apr-2026 | — | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Partially Delivered – 75% | 50% Paid – Milestone 2 Pending | 48% | 108 | Transmission line work pending
AGEL-S-033 | Dhule Solar Phase 2 – 100MW | Solar | Dhule | Maharashtra | 100 | FY2025-26 | Ongoing | 459.95 | 363.19 | 96.76 | 0 | 19-Oct-2026 | 28-Mar-2027 | — | Waaree Energies Ltd | Vikram Solar (545W HJT) | Partially Delivered – 75% | 75% Paid – Balance on Completion | 62% | 160 | Transmission line work pending
AGEL-S-034 | Barmer Solar Park – 50MW | Solar | Barmer | Rajasthan | 50 | FY2025-26 | Ongoing | 258.98 | 126.9 | 132.08 | 0 | 20-Dec-2025 | 24-Jul-2026 | — | Genus Power Infrastructures | Trina Solar (550W Vertex) | Partially Delivered – 75% | 10% Mobilisation Advance Paid | 85% | 216 | Transmission line work pending
AGEL-S-035 | Khavda Solar Phase 1 – 50MW | Solar | Khavda | Gujarat | 50 | FY2024-25 | Ongoing | 205.25 | 126.3 | 78.95 | 0 | 08-Jan-2026 | 28-May-2026 | — | Tata Projects Ltd | LONGi Solar (555W Hi-MO6) | PO Raised – Awaiting Dispatch | 30% Paid – Advance Released | 62% | 140 | Transmission line work pending
AGEL-S-036 | Fatehgarh Solar Park – 400MW | Solar | Fatehgarh | Rajasthan | 400 | FY2025-26 | Ongoing | 1715.1 | 1056.01 | 659.09 | 0 | 22-Jul-2026 | 22-Sep-2026 | — | Genus Power Infrastructures | LONGi Solar (555W Hi-MO6) | Partially Delivered – 50% | Payment on Hold – Dispute | 68% | 62 | Turbine erection in progress
AGEL-S-037 | Tumkur Solar Park – 50MW | Solar | Tumkur | Karnataka | 50 | FY2024-25 | Ongoing | 243.5 | 148.56 | 94.94 | 0 | 17-Mar-2026 | 03-Nov-2026 | — | KEC International | First Solar (440W Series 6) | In Transit | 10% Mobilisation Advance Paid | 79% | 231 | Statutory approvals awaited
AGEL-S-038 | Chitradurga Solar Phase 2 – 150MW | Solar | Chitradurga | Karnataka | 150 | FY2025-26 | Ongoing | 814.2 | 308.73 | 505.47 | 0 | 06-Apr-2025 | 01-Dec-2025 | — | L&T Construction | Waaree Energies (550W Mono PERC) | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 59% | 239 | Land acquisition in progress
AGEL-S-039 | Pokhran Solar Phase 3 – 200MW | Solar | Pokhran | Rajasthan | 200 | FY2024-25 | Ongoing | 1065.84 | 603.93 | 461.91 | 0 | 12-Apr-2026 | 26-Aug-2026 | — | KEC International | Vikram Solar (545W HJT) | In Transit | 10% Mobilisation Advance Paid | 69% | 136 | Land acquisition in progress
AGEL-S-040 | Jodhpur Solar Phase 1 – 100MW | Solar | Jodhpur | Rajasthan | 100 | FY2024-25 | Ongoing | 469.68 | 261.41 | 208.27 | 0 | 14-Dec-2026 | 25-May-2027 | — | Montecarlo Ltd | First Solar (440W Series 6) | In Transit | 50% Paid – Milestone 2 Pending | 35% | 162 | Financial closure in progress
AGEL-S-041 | Mundra Solar Phase 3 – 500MW | Solar | Mundra | Gujarat | 500 | FY2025-26 | Ongoing | 2672.91 | 1761.48 | 911.43 | 0 | 16-Jul-2026 | 07-Dec-2026 | — | KEC International | LONGi Solar (555W Hi-MO6) | In Transit | 30% Paid – Advance Released | 80% | 144 | Statutory approvals awaited
AGEL-S-042 | Patan Solar Park – 200MW | Solar | Patan | Gujarat | 200 | FY2024-25 | Ongoing | 881.51 | 375.38 | 506.13 | 0 | 20-Oct-2025 | 18-Jan-2026 | — | KEC International | Canadian Solar (550W HiKu7) | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 30% | 90 | Civil work ongoing
AGEL-S-043 | Osmanabad Solar Park – 200MW | Solar | Osmanabad | Maharashtra | 200 | FY2025-26 | Ongoing | 939.78 | 267.13 | 672.65 | 0 | 05-Dec-2025 | 22-May-2026 | — | Sterling and Wilson Pvt Ltd | REC Group (405W Alpha Pure-R) | In Transit | Payment on Hold – Dispute | 73% | 168 | Turbine erection in progress
AGEL-S-044 | Morbi Solar Park – 500MW | Solar | Morbi | Gujarat | 500 | FY2025-26 | Ongoing | 2292.49 | 1697.37 | 595.12 | 0 | 02-Nov-2025 | 12-Jun-2026 | — | Genus Power Infrastructures | Trina Solar (550W Vertex) | PO Raised – Awaiting Dispatch | Payment on Hold – Dispute | 73% | 222 | Statutory approvals awaited
AGEL-S-045 | Anantapur Solar Park – 200MW | Solar | Anantapur | Andhra Pradesh | 200 | FY2025-26 | Ongoing | 900.84 | 561.7 | 339.14 | 0 | 30-Jan-2025 | 08-Jun-2025 | — | L&T Construction | REC Group (405W Alpha Pure-R) | Partially Delivered – 50% | 10% Mobilisation Advance Paid | 71% | 129 | Land acquisition in progress
AGEL-S-046 | Rann of Kutch Solar Phase 3 – 400MW | Solar | Rann of Kutch | Gujarat | 400 | FY2024-25 | Ongoing | 1857.17 | 1349.73 | 507.44 | 0 | 27-Mar-2025 | 07-Oct-2025 | — | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Partially Delivered – 75% | 30% Paid – Advance Released | 43% | 194 | Module installation underway
AGEL-S-047 | Jaisalmer Solar Park – 500MW | Solar | Jaisalmer | Rajasthan | 500 | FY2025-26 | Ongoing | 2713.4 | 1307.48 | 1405.92 | 0 | 12-Oct-2025 | 22-May-2026 | — | SPML Infra Ltd | Waaree Energies (550W Mono PERC) | In Transit | 75% Paid – Balance on Completion | 30% | 222 | Financial closure in progress
AGEL-S-048 | Kurnool Solar Phase 3 – 200MW | Solar | Kurnool | Andhra Pradesh | 200 | FY2024-25 | Ongoing | 859.81 | 224.59 | 635.22 | 0 | 01-Feb-2025 | 05-May-2025 | — | Montecarlo Ltd | Adani Solar (540W TOPCon) | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 39% | 93 | Module installation underway
AGEL-S-049 | Bikaner Solar Phase 2 – 500MW | Solar | Bikaner | Rajasthan | 500 | FY2024-25 | Ongoing | 2722.8 | 1756.47 | 966.33 | 0 | 13-Sep-2026 | 17-Mar-2027 | — | Genus Power Infrastructures | Waaree Energies (550W Mono PERC) | Partially Delivered – 25% | 75% Paid – Balance on Completion | 40% | 185 | Transmission line work pending
AGEL-S-050 | Pavagada Solar Park – 400MW | Solar | Pavagada | Karnataka | 400 | FY2024-25 | Ongoing | 2014.37 | 1198.52 | 815.85 | 0 | 19-Mar-2025 | 16-Sep-2025 | — | Tata Projects Ltd | REC Group (405W Alpha Pure-R) | Partially Delivered – 25% | Payment on Hold – Dispute | 33% | 181 | Land acquisition in progress
AGEL-S-051 | Dhule Solar Phase 3 – 300MW | Solar | Dhule | Maharashtra | 300 | FY2026-27 | Planned | 1411.97 | 1.79 | 1410.18 | 0 | 12-Mar-2026 | 25-May-2027 | — | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Under Procurement | Payment on Hold – Dispute | 13% | 439 | Statutory approvals awaited
AGEL-S-052 | Barmer Solar Phase 3 – 150MW | Solar | Barmer | Rajasthan | 150 | FY2026-27 | Planned | 732.67 | 34.06 | 698.61 | 0 | 23-Sep-2027 | 21-Dec-2028 | — | Tata Projects Ltd | LONGi Solar (555W Hi-MO6) | Under Procurement | Payment on Hold – Dispute | 8% | 455 | Statutory approvals awaited
AGEL-S-053 | Khavda Solar Phase 3 – 200MW | Solar | Khavda | Gujarat | 200 | FY2026-27 | Planned | 898.41 | 29.2 | 869.21 | 0 | 11-Dec-2026 | 23-Jun-2027 | — | Waaree Energies Ltd | JA Solar (545W DeepBlue) | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 15% | 194 | Transmission line work pending
AGEL-S-054 | Fatehgarh Solar Phase 3 – 250MW | Solar | Fatehgarh | Rajasthan | 250 | FY2025-26 | Planned | 1202.03 | 58.73 | 1143.3 | 0 | 29-Mar-2026 | 26-Jan-2027 | — | Montecarlo Ltd | Jinko Solar (545W Tiger Neo) | Not Yet Procured | Invoice Raised – Awaiting Approval | 7% | 303 | Land acquisition in progress
AGEL-S-055 | Tumkur Solar Park – 100MW | Solar | Tumkur | Karnataka | 100 | FY2026-27 | Planned | 422.87 | 24.59 | 398.28 | 0 | 10-Dec-2027 | 09-Oct-2028 | — | Vikram Solar Ltd | Canadian Solar (550W HiKu7) | Not Yet Procured | Not Started | 15% | 304 | Financial closure in progress
AGEL-W-056 | Khavda Wind Phase 2 – 50MW | Wind | Khavda | Gujarat | 50 | FY2021-22 | Commissioned | 234.18 | 228.71 | 5.47 | 45.12 | 19-Dec-2022 | — | 10-Jan-2023 | Suzlon Energy Ltd | Vestas V150-4.5MW | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-057 | Jodhpur Wind Phase 3 – 300MW | Wind | Jodhpur | Rajasthan | 300 | FY2022-23 | Commissioned | 1535.55 | 1470.37 | 65.18 | 344.04 | 29-Jul-2021 | — | 30-Jul-2021 | Suzlon Energy Ltd | Vestas V150-4.5MW | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-058 | Tumkur Wind Park – 200MW | Wind | Tumkur | Karnataka | 200 | FY2021-22 | Commissioned | 863.71 | 838.11 | 25.6 | 160.1 | 29-Jan-2023 | — | 01-Apr-2023 | Senvion India Pvt Ltd | Vestas V150-4.5MW | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-059 | Patan Wind Phase 1 – 50MW | Wind | Patan | Gujarat | 50 | FY2023-24 | Commissioned | 257.69 | 249.82 | 7.87 | 66.37 | 15-Feb-2023 | — | 03-May-2023 | Envision Energy India | Windworld W-3000 | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-W-060 | Anantapur Wind Phase 2 – 150MW | Wind | Anantapur | Andhra Pradesh | 150 | FY2022-23 | Commissioned | 860.43 | 798.43 | 62 | 220.51 | 15-Feb-2021 | — | 04-May-2021 | GE Vernova India | Siemens Gamesa SG 5.0-145 | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-061 | Morbi Wind Park – 100MW | Wind | Morbi | Gujarat | 100 | FY2023-24 | Commissioned | 420.43 | 401.95 | 18.48 | 100.64 | 14-May-2021 | — | 03-Jun-2021 | Suzlon Energy Ltd | GE Vernova 3.6MW-137 | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-W-062 | Rann of Kutch Wind Phase 3 – 150MW | Wind | Rann of Kutch | Gujarat | 150 | FY2022-23 | Commissioned | 686.02 | 645.66 | 40.36 | 177.76 | 28-Feb-2021 | — | 26-May-2021 | ReGen Powertech Pvt Ltd | Siemens Gamesa SG 5.0-145 | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-063 | Bikaner Wind Park – 250MW | Wind | Bikaner | Rajasthan | 250 | FY2021-22 | Commissioned | 1078.56 | 1006.59 | 71.97 | 227.32 | 11-Jun-2022 | — | 29-Jun-2022 | Envision Energy India | Siemens Gamesa SG 5.0-145 | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-W-064 | Dhule Wind Phase 3 – 200MW | Wind | Dhule | Maharashtra | 200 | FY2022-23 | Commissioned | 1012.79 | 967.24 | 45.55 | 242.87 | 09-May-2022 | — | 12-Jul-2022 | Windworld India Ltd | Vestas V150-4.5MW | Fully Delivered | 75% Paid – Balance on Completion | 100% | 0 | On track
AGEL-W-065 | Mundra Wind Park – 50MW | Wind | Mundra | Gujarat | 50 | FY2023-24 | Commissioned | 275.71 | 266.36 | 9.35 | 70.67 | 18-Nov-2020 | — | 12-Feb-2021 | Envision Energy India | Windworld W-3000 | Fully Delivered | Fully Paid | 100% | 0 | On track
AGEL-W-066 | Chitradurga Wind Park – 150MW | Wind | Chitradurga | Karnataka | 150 | FY2025-26 | Ongoing | 710.64 | 213.32 | 497.32 | 0 | 13-Oct-2026 | 08-Jun-2027 | — | Windworld India Ltd | Siemens Gamesa SG 5.0-145 | In Transit | 30% Paid – Advance Released | 64% | 238 | Civil work ongoing
AGEL-W-067 | Jaisalmer Wind Phase 2 – 150MW | Wind | Jaisalmer | Rajasthan | 150 | FY2025-26 | Ongoing | 783.05 | 432.68 | 350.37 | 0 | 10-Nov-2026 | 22-Mar-2027 | — | GE Vernova India | Enercon E-160 EP5 | Partially Delivered – 75% | 30% Paid – Advance Released | 78% | 132 | Pending grid connectivity approval
AGEL-W-068 | Fatehgarh Wind Phase 1 – 200MW | Wind | Fatehgarh | Rajasthan | 200 | FY2025-26 | Ongoing | 856.27 | 384.45 | 471.82 | 0 | 28-Feb-2026 | 12-Apr-2026 | — | Vestas Wind Systems India | Vestas V150-4.5MW | In Transit | 75% Paid – Balance on Completion | 83% | 43 | Civil work ongoing
AGEL-W-069 | Osmanabad Wind Phase 3 – 150MW | Wind | Osmanabad | Maharashtra | 150 | FY2025-26 | Ongoing | 818.96 | 478.99 | 339.97 | 0 | 05-May-2025 | 11-Jun-2025 | — | Enercon India Ltd | Suzlon S144 (3MW) | Partially Delivered – 50% | 30% Paid – Advance Released | 50% | 37 | Turbine erection in progress
AGEL-W-070 | Pokhran Wind Park – 50MW | Wind | Pokhran | Rajasthan | 50 | FY2024-25 | Ongoing | 248.58 | 83.2 | 165.38 | 0 | 18-Apr-2026 | 17-Jun-2026 | — | ReGen Powertech Pvt Ltd | Windworld W-3000 | PO Raised – Awaiting Dispatch | 30% Paid – Advance Released | 57% | 60 | Statutory approvals awaited
AGEL-W-071 | Barmer Wind Phase 1 – 100MW | Wind | Barmer | Rajasthan | 100 | FY2025-26 | Ongoing | 489.91 | 323.57 | 166.34 | 0 | 15-Jul-2025 | 06-Apr-2026 | — | ReGen Powertech Pvt Ltd | Enercon E-160 EP5 | Partially Delivered – 75% | 30% Paid – Advance Released | 37% | 265 | Transmission line work pending
AGEL-W-072 | Pavagada Wind Park – 50MW | Wind | Pavagada | Karnataka | 50 | FY2025-26 | Ongoing | 274.92 | 142.77 | 132.15 | 0 | 25-Aug-2026 | 19-Feb-2027 | — | Envision Energy India | Enercon E-160 EP5 | In Transit | Payment on Hold – Dispute | 39% | 178 | Financial closure in progress
AGEL-W-073 | Kurnool Wind Phase 2 – 250MW | Wind | Kurnool | Andhra Pradesh | 250 | FY2026-27 | Planned | 1293.27 | 30.88 | 1262.39 | 0 | 26-Nov-2026 | 29-Aug-2027 | — | Suzlon Energy Ltd | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 12% | 276 | Statutory approvals awaited
AGEL-W-074 | Khavda Wind Phase 2 – 300MW | Wind | Khavda | Gujarat | 300 | FY2026-27 | Planned | 1551.94 | 76.87 | 1475.07 | 0 | 11-Nov-2027 | 07-Apr-2029 | — | Senvion India Pvt Ltd | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | Not Started | 1% | 513 | Pending grid connectivity approval
AGEL-W-075 | Jodhpur Wind Park – 200MW | Wind | Jodhpur | Rajasthan | 200 | FY2026-27 | Planned | 874.79 | 57.28 | 817.51 | 0 | 16-Jan-2026 | 26-Sep-2026 | — | GE Vernova India | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 4% | 253 | Turbine erection in progress

## Summary Dashboard
AGEL — Executive Project Summary Dashboard
Portfolio Overview
Total Projects | 75
Solar Projects | 55
Wind Projects | 20
Commissioned | 40
Ongoing | 27
Planned | 8
Total Capacity (MW) | 7900
Total Budget Allocated (₹ Cr) | 76012.84
Total Budget Used (₹ Cr) | 54099.64
Total Revenue (₹ Cr) | 9045.97
Projects by State
State | Projects | Total Capacity (MW) | Total Budget (₹ Cr)
Andhra Pradesh | 8 | 1800 | 8597.08
Gujarat | 21 | 4150 | 19555.54
Karnataka | 13 | 2800 | 13887.51
Maharashtra | 8 | 1600 | 7586.45
Rajasthan | 25 | 5400 | 26386.26

## Ongoing Tracker
AGEL — Ongoing Projects Tracker
Project ID | Project Name | Location | State | Capacity (MW) | FY Year | Budget Allocated (₹ Cr) | Budget Used (₹ Cr) | Scheduled Comm. Date | Expected Comm. Date | Contractor Name | Material Status | Contractor Payment Status | Project Completion (%) | Remarks
AGEL-S-031 | Bikaner Solar Park – 50MW | Bikaner | Rajasthan | 50 | FY2025-26 | 250.24 | 163.73 | 26-Feb-2026 | 19-Oct-2026 | Tata Projects Ltd | Partially Delivered – 25% | 50% Paid – Milestone 2 Pending | 51% | Land acquisition in progress
AGEL-S-032 | Pavagada Solar Park – 500MW | Pavagada | Karnataka | 500 | FY2025-26 | 2615.4 | 1907.22 | 25-Dec-2025 | 12-Apr-2026 | Goldi Solar Pvt Ltd | Partially Delivered – 75% | 50% Paid – Milestone 2 Pending | 48% | Transmission line work pending
AGEL-S-033 | Dhule Solar Phase 2 – 100MW | Dhule | Maharashtra | 100 | FY2025-26 | 459.95 | 363.19 | 19-Oct-2026 | 28-Mar-2027 | Waaree Energies Ltd | Partially Delivered – 75% | 75% Paid – Balance on Completion | 62% | Transmission line work pending
AGEL-S-034 | Barmer Solar Park – 50MW | Barmer | Rajasthan | 50 | FY2025-26 | 258.98 | 126.9 | 20-Dec-2025 | 24-Jul-2026 | Genus Power Infrastructures | Partially Delivered – 75% | 10% Mobilisation Advance Paid | 85% | Transmission line work pending
AGEL-S-035 | Khavda Solar Phase 1 – 50MW | Khavda | Gujarat | 50 | FY2024-25 | 205.25 | 126.3 | 08-Jan-2026 | 28-May-2026 | Tata Projects Ltd | PO Raised – Awaiting Dispatch | 30% Paid – Advance Released | 62% | Transmission line work pending
AGEL-S-036 | Fatehgarh Solar Park – 400MW | Fatehgarh | Rajasthan | 400 | FY2025-26 | 1715.1 | 1056.01 | 22-Jul-2026 | 22-Sep-2026 | Genus Power Infrastructures | Partially Delivered – 50% | Payment on Hold – Dispute | 68% | Turbine erection in progress
AGEL-S-037 | Tumkur Solar Park – 50MW | Tumkur | Karnataka | 50 | FY2024-25 | 243.5 | 148.56 | 17-Mar-2026 | 03-Nov-2026 | KEC International | In Transit | 10% Mobilisation Advance Paid | 79% | Statutory approvals awaited
AGEL-S-038 | Chitradurga Solar Phase 2 – 150MW | Chitradurga | Karnataka | 150 | FY2025-26 | 814.2 | 308.73 | 06-Apr-2025 | 01-Dec-2025 | L&T Construction | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 59% | Land acquisition in progress
AGEL-S-039 | Pokhran Solar Phase 3 – 200MW | Pokhran | Rajasthan | 200 | FY2024-25 | 1065.84 | 603.93 | 12-Apr-2026 | 26-Aug-2026 | KEC International | In Transit | 10% Mobilisation Advance Paid | 69% | Land acquisition in progress
AGEL-S-040 | Jodhpur Solar Phase 1 – 100MW | Jodhpur | Rajasthan | 100 | FY2024-25 | 469.68 | 261.41 | 14-Dec-2026 | 25-May-2027 | Montecarlo Ltd | In Transit | 50% Paid – Milestone 2 Pending | 35% | Financial closure in progress
AGEL-S-041 | Mundra Solar Phase 3 – 500MW | Mundra | Gujarat | 500 | FY2025-26 | 2672.91 | 1761.48 | 16-Jul-2026 | 07-Dec-2026 | KEC International | In Transit | 30% Paid – Advance Released | 80% | Statutory approvals awaited
AGEL-S-042 | Patan Solar Park – 200MW | Patan | Gujarat | 200 | FY2024-25 | 881.51 | 375.38 | 20-Oct-2025 | 18-Jan-2026 | KEC International | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 30% | Civil work ongoing
AGEL-S-043 | Osmanabad Solar Park – 200MW | Osmanabad | Maharashtra | 200 | FY2025-26 | 939.78 | 267.13 | 05-Dec-2025 | 22-May-2026 | Sterling and Wilson Pvt Ltd | In Transit | Payment on Hold – Dispute | 73% | Turbine erection in progress
AGEL-S-044 | Morbi Solar Park – 500MW | Morbi | Gujarat | 500 | FY2025-26 | 2292.49 | 1697.37 | 02-Nov-2025 | 12-Jun-2026 | Genus Power Infrastructures | PO Raised – Awaiting Dispatch | Payment on Hold – Dispute | 73% | Statutory approvals awaited
AGEL-S-045 | Anantapur Solar Park – 200MW | Anantapur | Andhra Pradesh | 200 | FY2025-26 | 900.84 | 561.7 | 30-Jan-2025 | 08-Jun-2025 | L&T Construction | Partially Delivered – 50% | 10% Mobilisation Advance Paid | 71% | Land acquisition in progress
AGEL-S-046 | Rann of Kutch Solar Phase 3 – 400MW | Rann of Kutch | Gujarat | 400 | FY2024-25 | 1857.17 | 1349.73 | 27-Mar-2025 | 07-Oct-2025 | Goldi Solar Pvt Ltd | Partially Delivered – 75% | 30% Paid – Advance Released | 43% | Module installation underway
AGEL-S-047 | Jaisalmer Solar Park – 500MW | Jaisalmer | Rajasthan | 500 | FY2025-26 | 2713.4 | 1307.48 | 12-Oct-2025 | 22-May-2026 | SPML Infra Ltd | In Transit | 75% Paid – Balance on Completion | 30% | Financial closure in progress
AGEL-S-048 | Kurnool Solar Phase 3 – 200MW | Kurnool | Andhra Pradesh | 200 | FY2024-25 | 859.81 | 224.59 | 01-Feb-2025 | 05-May-2025 | Montecarlo Ltd | Partially Delivered – 50% | 50% Paid – Milestone 2 Pending | 39% | Module installation underway
AGEL-S-049 | Bikaner Solar Phase 2 – 500MW | Bikaner | Rajasthan | 500 | FY2024-25 | 2722.8 | 1756.47 | 13-Sep-2026 | 17-Mar-2027 | Genus Power Infrastructures | Partially Delivered – 25% | 75% Paid – Balance on Completion | 40% | Transmission line work pending
AGEL-S-050 | Pavagada Solar Park – 400MW | Pavagada | Karnataka | 400 | FY2024-25 | 2014.37 | 1198.52 | 19-Mar-2025 | 16-Sep-2025 | Tata Projects Ltd | Partially Delivered – 25% | Payment on Hold – Dispute | 33% | Land acquisition in progress
AGEL-S-051 | Dhule Solar Phase 3 – 300MW | Dhule | Maharashtra | 300 | FY2026-27 | 1411.97 | 1.79 | 12-Mar-2026 | 25-May-2027 | Goldi Solar Pvt Ltd | Under Procurement | Payment on Hold – Dispute | 13% | Statutory approvals awaited
AGEL-S-052 | Barmer Solar Phase 3 – 150MW | Barmer | Rajasthan | 150 | FY2026-27 | 732.67 | 34.06 | 23-Sep-2027 | 21-Dec-2028 | Tata Projects Ltd | Under Procurement | Payment on Hold – Dispute | 8% | Statutory approvals awaited
AGEL-S-053 | Khavda Solar Phase 3 – 200MW | Khavda | Gujarat | 200 | FY2026-27 | 898.41 | 29.2 | 11-Dec-2026 | 23-Jun-2027 | Waaree Energies Ltd | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 15% | Transmission line work pending
AGEL-S-054 | Fatehgarh Solar Phase 3 – 250MW | Fatehgarh | Rajasthan | 250 | FY2025-26 | 1202.03 | 58.73 | 29-Mar-2026 | 26-Jan-2027 | Montecarlo Ltd | Not Yet Procured | Invoice Raised – Awaiting Approval | 7% | Land acquisition in progress
AGEL-S-055 | Tumkur Solar Park – 100MW | Tumkur | Karnataka | 100 | FY2026-27 | 422.87 | 24.59 | 10-Dec-2027 | 09-Oct-2028 | Vikram Solar Ltd | Not Yet Procured | Not Started | 15% | Financial closure in progress
AGEL-W-066 | Chitradurga Wind Park – 150MW | Chitradurga | Karnataka | 150 | FY2025-26 | 710.64 | 213.32 | 13-Oct-2026 | 08-Jun-2027 | Windworld India Ltd | In Transit | 30% Paid – Advance Released | 64% | Civil work ongoing
AGEL-W-067 | Jaisalmer Wind Phase 2 – 150MW | Jaisalmer | Rajasthan | 150 | FY2025-26 | 783.05 | 432.68 | 10-Nov-2026 | 22-Mar-2027 | GE Vernova India | Partially Delivered – 75% | 30% Paid – Advance Released | 78% | Pending grid connectivity approval
AGEL-W-068 | Fatehgarh Wind Phase 1 – 200MW | Fatehgarh | Rajasthan | 200 | FY2025-26 | 856.27 | 384.45 | 28-Feb-2026 | 12-Apr-2026 | Vestas Wind Systems India | In Transit | 75% Paid – Balance on Completion | 83% | Civil work ongoing
AGEL-W-069 | Osmanabad Wind Phase 3 – 150MW | Osmanabad | Maharashtra | 150 | FY2025-26 | 818.96 | 478.99 | 05-May-2025 | 11-Jun-2025 | Enercon India Ltd | Partially Delivered – 50% | 30% Paid – Advance Released | 50% | Turbine erection in progress
AGEL-W-070 | Pokhran Wind Park – 50MW | Pokhran | Rajasthan | 50 | FY2024-25 | 248.58 | 83.2 | 18-Apr-2026 | 17-Jun-2026 | ReGen Powertech Pvt Ltd | PO Raised – Awaiting Dispatch | 30% Paid – Advance Released | 57% | Statutory approvals awaited
AGEL-W-071 | Barmer Wind Phase 1 – 100MW | Barmer | Rajasthan | 100 | FY2025-26 | 489.91 | 323.57 | 15-Jul-2025 | 06-Apr-2026 | ReGen Powertech Pvt Ltd | Partially Delivered – 75% | 30% Paid – Advance Released | 37% | Transmission line work pending
AGEL-W-072 | Pavagada Wind Park – 50MW | Pavagada | Karnataka | 50 | FY2025-26 | 274.92 | 142.77 | 25-Aug-2026 | 19-Feb-2027 | Envision Energy India | In Transit | Payment on Hold – Dispute | 39% | Financial closure in progress
AGEL-W-073 | Kurnool Wind Phase 2 – 250MW | Kurnool | Andhra Pradesh | 250 | FY2026-27 | 1293.27 | 30.88 | 26-Nov-2026 | 29-Aug-2027 | Suzlon Energy Ltd | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 12% | Statutory approvals awaited
AGEL-W-074 | Khavda Wind Phase 2 – 300MW | Khavda | Gujarat | 300 | FY2026-27 | 1551.94 | 76.87 | 11-Nov-2027 | 07-Apr-2029 | Senvion India Pvt Ltd | PO Raised – Awaiting Dispatch | Not Started | 1% | Pending grid connectivity approval
AGEL-W-075 | Jodhpur Wind Park – 200MW | Jodhpur | Rajasthan | 200 | FY2026-27 | 874.79 | 57.28 | 16-Jan-2026 | 26-Sep-2026 | GE Vernova India | PO Raised – Awaiting Dispatch | Invoice Raised – Awaiting Approval | 4% | Turbine erection in progress

## Material & Payment
AGEL — Material & Contractor Payment Status
Project ID | Project Name | Project Type | Contractor Name | Material (Module/Turbine) | Material Status | Budget Allocated (₹ Cr) | Contractor Payment Status | Project Completion (%) | Category
AGEL-S-001 | Tumkur Solar Phase 3 – 200MW | Solar | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Fully Delivered | 983.75 | Fully Paid | 100% | Commissioned
AGEL-S-002 | Chitradurga Solar Park – 250MW | Solar | Sterling and Wilson Pvt Ltd | Jinko Solar (545W Tiger Neo) | Fully Delivered | 1201.97 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-003 | Pokhran Solar Phase 2 – 100MW | Solar | Sterling and Wilson Pvt Ltd | Trina Solar (550W Vertex) | Fully Delivered | 518.96 | Fully Paid | 100% | Commissioned
AGEL-S-004 | Jodhpur Solar Phase 1 – 250MW | Solar | KEC International | LONGi Solar (555W Hi-MO6) | Fully Delivered | 1231.36 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-005 | Mundra Solar Phase 1 – 100MW | Solar | Vikram Solar Ltd | Waaree Energies (550W Mono PERC) | Fully Delivered | 493.96 | Fully Paid | 100% | Commissioned
AGEL-S-006 | Patan Solar Phase 2 – 200MW | Solar | KEC International | Jinko Solar (545W Tiger Neo) | Fully Delivered | 907.51 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-007 | Osmanabad Solar Phase 3 – 400MW | Solar | Genus Power Infrastructures | Canadian Solar (550W HiKu7) | Fully Delivered | 1769.36 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-008 | Morbi Solar Park – 300MW | Solar | Goldi Solar Pvt Ltd | REC Group (405W Alpha Pure-R) | Fully Delivered | 1303.64 | Fully Paid | 100% | Commissioned
AGEL-S-009 | Anantapur Solar Park – 100MW | Solar | SPML Infra Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | 460.23 | Fully Paid | 100% | Commissioned
AGEL-S-010 | Rann of Kutch Solar Park – 300MW | Solar | SPML Infra Ltd | Adani Solar (540W TOPCon) | Fully Delivered | 1261.56 | Fully Paid | 100% | Commissioned
AGEL-S-011 | Jaisalmer Solar Phase 3 – 250MW | Solar | Genus Power Infrastructures | JA Solar (545W DeepBlue) | Fully Delivered | 1199.57 | Fully Paid | 100% | Commissioned
AGEL-S-012 | Kurnool Solar Park – 500MW | Solar | Montecarlo Ltd | Adani Solar (540W TOPCon) | Fully Delivered | 2146.34 | Fully Paid | 100% | Commissioned
AGEL-S-013 | Bikaner Solar Park – 150MW | Solar | Waaree Energies Ltd | Canadian Solar (550W HiKu7) | Fully Delivered | 756.64 | Fully Paid | 100% | Commissioned
AGEL-S-014 | Pavagada Solar Phase 3 – 300MW | Solar | Genus Power Infrastructures | Trina Solar (550W Vertex) | Fully Delivered | 1367.85 | Fully Paid | 100% | Commissioned
AGEL-S-015 | Dhule Solar Park – 50MW | Solar | Waaree Energies Ltd | Jinko Solar (545W Tiger Neo) | Fully Delivered | 215.39 | Fully Paid | 100% | Commissioned
AGEL-S-016 | Barmer Solar Phase 3 – 200MW | Solar | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Fully Delivered | 1091.08 | Fully Paid | 100% | Commissioned
AGEL-S-017 | Khavda Solar Phase 3 – 400MW | Solar | KEC International | Trina Solar (550W Vertex) | Fully Delivered | 1937.68 | Fully Paid | 100% | Commissioned
AGEL-S-018 | Fatehgarh Solar Park – 500MW | Solar | Sterling and Wilson Pvt Ltd | First Solar (440W Series 6) | Fully Delivered | 2299.85 | Fully Paid | 100% | Commissioned
AGEL-S-019 | Tumkur Solar Phase 1 – 50MW | Solar | Goldi Solar Pvt Ltd | Waaree Energies (550W Mono PERC) | Fully Delivered | 248.51 | Fully Paid | 100% | Commissioned
AGEL-S-020 | Chitradurga Solar Park – 400MW | Solar | L&T Construction | Trina Solar (550W Vertex) | Fully Delivered | 2125.82 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-021 | Pokhran Solar Park – 250MW | Solar | Sterling and Wilson Pvt Ltd | First Solar (440W Series 6) | Fully Delivered | 1072.87 | Fully Paid | 100% | Commissioned
AGEL-S-022 | Jodhpur Solar Phase 1 – 100MW | Solar | Genus Power Infrastructures | REC Group (405W Alpha Pure-R) | Fully Delivered | 557.89 | Fully Paid | 100% | Commissioned
AGEL-S-023 | Mundra Solar Phase 2 – 50MW | Solar | Waaree Energies Ltd | Canadian Solar (550W HiKu7) | Fully Delivered | 284.78 | Fully Paid | 100% | Commissioned
AGEL-S-024 | Patan Solar Phase 2 – 150MW | Solar | Tata Projects Ltd | First Solar (440W Series 6) | Fully Delivered | 632.24 | Fully Paid | 100% | Commissioned
AGEL-S-025 | Osmanabad Solar Phase 1 – 200MW | Solar | Genus Power Infrastructures | First Solar (440W Series 6) | Fully Delivered | 958.25 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-S-026 | Morbi Solar Phase 3 – 50MW | Solar | Waaree Energies Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | 231.16 | Fully Paid | 100% | Commissioned
AGEL-S-027 | Anantapur Solar Phase 1 – 200MW | Solar | Goldi Solar Pvt Ltd | LONGi Solar (555W Hi-MO6) | Fully Delivered | 996.33 | Fully Paid | 100% | Commissioned
AGEL-S-028 | Rann of Kutch Solar Park – 50MW | Solar | Tata Projects Ltd | Adani Solar (540W TOPCon) | Fully Delivered | 269.3 | Fully Paid | 100% | Commissioned
AGEL-S-029 | Jaisalmer Solar Phase 2 – 150MW | Solar | Vikram Solar Ltd | Trina Solar (550W Vertex) | Fully Delivered | 660.59 | Fully Paid | 100% | Commissioned
AGEL-S-030 | Kurnool Solar Phase 2 – 200MW | Solar | L&T Construction | Canadian Solar (550W HiKu7) | Fully Delivered | 1079.83 | Fully Paid | 100% | Commissioned
AGEL-S-031 | Bikaner Solar Park – 50MW | Solar | Tata Projects Ltd | Canadian Solar (550W HiKu7) | Partially Delivered – 25% | 250.24 | 50% Paid – Milestone 2 Pending | 51% | Ongoing
AGEL-S-032 | Pavagada Solar Park – 500MW | Solar | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Partially Delivered – 75% | 2615.4 | 50% Paid – Milestone 2 Pending | 48% | Ongoing
AGEL-S-033 | Dhule Solar Phase 2 – 100MW | Solar | Waaree Energies Ltd | Vikram Solar (545W HJT) | Partially Delivered – 75% | 459.95 | 75% Paid – Balance on Completion | 62% | Ongoing
AGEL-S-034 | Barmer Solar Park – 50MW | Solar | Genus Power Infrastructures | Trina Solar (550W Vertex) | Partially Delivered – 75% | 258.98 | 10% Mobilisation Advance Paid | 85% | Ongoing
AGEL-S-035 | Khavda Solar Phase 1 – 50MW | Solar | Tata Projects Ltd | LONGi Solar (555W Hi-MO6) | PO Raised – Awaiting Dispatch | 205.25 | 30% Paid – Advance Released | 62% | Ongoing
AGEL-S-036 | Fatehgarh Solar Park – 400MW | Solar | Genus Power Infrastructures | LONGi Solar (555W Hi-MO6) | Partially Delivered – 50% | 1715.1 | Payment on Hold – Dispute | 68% | Ongoing
AGEL-S-037 | Tumkur Solar Park – 50MW | Solar | KEC International | First Solar (440W Series 6) | In Transit | 243.5 | 10% Mobilisation Advance Paid | 79% | Ongoing
AGEL-S-038 | Chitradurga Solar Phase 2 – 150MW | Solar | L&T Construction | Waaree Energies (550W Mono PERC) | Partially Delivered – 50% | 814.2 | 50% Paid – Milestone 2 Pending | 59% | Ongoing
AGEL-S-039 | Pokhran Solar Phase 3 – 200MW | Solar | KEC International | Vikram Solar (545W HJT) | In Transit | 1065.84 | 10% Mobilisation Advance Paid | 69% | Ongoing
AGEL-S-040 | Jodhpur Solar Phase 1 – 100MW | Solar | Montecarlo Ltd | First Solar (440W Series 6) | In Transit | 469.68 | 50% Paid – Milestone 2 Pending | 35% | Ongoing
AGEL-S-041 | Mundra Solar Phase 3 – 500MW | Solar | KEC International | LONGi Solar (555W Hi-MO6) | In Transit | 2672.91 | 30% Paid – Advance Released | 80% | Ongoing
AGEL-S-042 | Patan Solar Park – 200MW | Solar | KEC International | Canadian Solar (550W HiKu7) | Partially Delivered – 50% | 881.51 | 50% Paid – Milestone 2 Pending | 30% | Ongoing
AGEL-S-043 | Osmanabad Solar Park – 200MW | Solar | Sterling and Wilson Pvt Ltd | REC Group (405W Alpha Pure-R) | In Transit | 939.78 | Payment on Hold – Dispute | 73% | Ongoing
AGEL-S-044 | Morbi Solar Park – 500MW | Solar | Genus Power Infrastructures | Trina Solar (550W Vertex) | PO Raised – Awaiting Dispatch | 2292.49 | Payment on Hold – Dispute | 73% | Ongoing
AGEL-S-045 | Anantapur Solar Park – 200MW | Solar | L&T Construction | REC Group (405W Alpha Pure-R) | Partially Delivered – 50% | 900.84 | 10% Mobilisation Advance Paid | 71% | Ongoing
AGEL-S-046 | Rann of Kutch Solar Phase 3 – 400MW | Solar | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Partially Delivered – 75% | 1857.17 | 30% Paid – Advance Released | 43% | Ongoing
AGEL-S-047 | Jaisalmer Solar Park – 500MW | Solar | SPML Infra Ltd | Waaree Energies (550W Mono PERC) | In Transit | 2713.4 | 75% Paid – Balance on Completion | 30% | Ongoing
AGEL-S-048 | Kurnool Solar Phase 3 – 200MW | Solar | Montecarlo Ltd | Adani Solar (540W TOPCon) | Partially Delivered – 50% | 859.81 | 50% Paid – Milestone 2 Pending | 39% | Ongoing
AGEL-S-049 | Bikaner Solar Phase 2 – 500MW | Solar | Genus Power Infrastructures | Waaree Energies (550W Mono PERC) | Partially Delivered – 25% | 2722.8 | 75% Paid – Balance on Completion | 40% | Ongoing
AGEL-S-050 | Pavagada Solar Park – 400MW | Solar | Tata Projects Ltd | REC Group (405W Alpha Pure-R) | Partially Delivered – 25% | 2014.37 | Payment on Hold – Dispute | 33% | Ongoing
AGEL-S-051 | Dhule Solar Phase 3 – 300MW | Solar | Goldi Solar Pvt Ltd | JA Solar (545W DeepBlue) | Under Procurement | 1411.97 | Payment on Hold – Dispute | 13% | Planned
AGEL-S-052 | Barmer Solar Phase 3 – 150MW | Solar | Tata Projects Ltd | LONGi Solar (555W Hi-MO6) | Under Procurement | 732.67 | Payment on Hold – Dispute | 8% | Planned
AGEL-S-053 | Khavda Solar Phase 3 – 200MW | Solar | Waaree Energies Ltd | JA Solar (545W DeepBlue) | PO Raised – Awaiting Dispatch | 898.41 | Invoice Raised – Awaiting Approval | 15% | Planned
AGEL-S-054 | Fatehgarh Solar Phase 3 – 250MW | Solar | Montecarlo Ltd | Jinko Solar (545W Tiger Neo) | Not Yet Procured | 1202.03 | Invoice Raised – Awaiting Approval | 7% | Planned
AGEL-S-055 | Tumkur Solar Park – 100MW | Solar | Vikram Solar Ltd | Canadian Solar (550W HiKu7) | Not Yet Procured | 422.87 | Not Started | 15% | Planned
AGEL-W-056 | Khavda Wind Phase 2 – 50MW | Wind | Suzlon Energy Ltd | Vestas V150-4.5MW | Fully Delivered | 234.18 | Fully Paid | 100% | Commissioned
AGEL-W-057 | Jodhpur Wind Phase 3 – 300MW | Wind | Suzlon Energy Ltd | Vestas V150-4.5MW | Fully Delivered | 1535.55 | Fully Paid | 100% | Commissioned
AGEL-W-058 | Tumkur Wind Park – 200MW | Wind | Senvion India Pvt Ltd | Vestas V150-4.5MW | Fully Delivered | 863.71 | Fully Paid | 100% | Commissioned
AGEL-W-059 | Patan Wind Phase 1 – 50MW | Wind | Envision Energy India | Windworld W-3000 | Fully Delivered | 257.69 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-W-060 | Anantapur Wind Phase 2 – 150MW | Wind | GE Vernova India | Siemens Gamesa SG 5.0-145 | Fully Delivered | 860.43 | Fully Paid | 100% | Commissioned
AGEL-W-061 | Morbi Wind Park – 100MW | Wind | Suzlon Energy Ltd | GE Vernova 3.6MW-137 | Fully Delivered | 420.43 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-W-062 | Rann of Kutch Wind Phase 3 – 150MW | Wind | ReGen Powertech Pvt Ltd | Siemens Gamesa SG 5.0-145 | Fully Delivered | 686.02 | Fully Paid | 100% | Commissioned
AGEL-W-063 | Bikaner Wind Park – 250MW | Wind | Envision Energy India | Siemens Gamesa SG 5.0-145 | Fully Delivered | 1078.56 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-W-064 | Dhule Wind Phase 3 – 200MW | Wind | Windworld India Ltd | Vestas V150-4.5MW | Fully Delivered | 1012.79 | 75% Paid – Balance on Completion | 100% | Commissioned
AGEL-W-065 | Mundra Wind Park – 50MW | Wind | Envision Energy India | Windworld W-3000 | Fully Delivered | 275.71 | Fully Paid | 100% | Commissioned
AGEL-W-066 | Chitradurga Wind Park – 150MW | Wind | Windworld India Ltd | Siemens Gamesa SG 5.0-145 | In Transit | 710.64 | 30% Paid – Advance Released | 64% | Ongoing
AGEL-W-067 | Jaisalmer Wind Phase 2 – 150MW | Wind | GE Vernova India | Enercon E-160 EP5 | Partially Delivered – 75% | 783.05 | 30% Paid – Advance Released | 78% | Ongoing
AGEL-W-068 | Fatehgarh Wind Phase 1 – 200MW | Wind | Vestas Wind Systems India | Vestas V150-4.5MW | In Transit | 856.27 | 75% Paid – Balance on Completion | 83% | Ongoing
AGEL-W-069 | Osmanabad Wind Phase 3 – 150MW | Wind | Enercon India Ltd | Suzlon S144 (3MW) | Partially Delivered – 50% | 818.96 | 30% Paid – Advance Released | 50% | Ongoing
AGEL-W-070 | Pokhran Wind Park – 50MW | Wind | ReGen Powertech Pvt Ltd | Windworld W-3000 | PO Raised – Awaiting Dispatch | 248.58 | 30% Paid – Advance Released | 57% | Ongoing
AGEL-W-071 | Barmer Wind Phase 1 – 100MW | Wind | ReGen Powertech Pvt Ltd | Enercon E-160 EP5 | Partially Delivered – 75% | 489.91 | 30% Paid – Advance Released | 37% | Ongoing
AGEL-W-072 | Pavagada Wind Park – 50MW | Wind | Envision Energy India | Enercon E-160 EP5 | In Transit | 274.92 | Payment on Hold – Dispute | 39% | Ongoing
AGEL-W-073 | Kurnool Wind Phase 2 – 250MW | Wind | Suzlon Energy Ltd | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | 1293.27 | Invoice Raised – Awaiting Approval | 12% | Planned
AGEL-W-074 | Khavda Wind Phase 2 – 300MW | Wind | Senvion India Pvt Ltd | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | 1551.94 | Not Started | 1% | Planned
AGEL-W-075 | Jodhpur Wind Park – 200MW | Wind | GE Vernova India | Enercon E-160 EP5 | PO Raised – Awaiting Dispatch | 874.79 | Invoice Raised – Awaiting Approval | 4% | Planned